# NUPCO H2-2026 RFP — Bid Committee Minutes (War-Room #2)

30 June 2026, 15:00-16:30, Boardroom | Chair: CEO | Present: CFO, CEO Pharma Logistics, BU CEO Distribution, Head of Institutional Sales, Legal | Ref: BC-2026-02

## Decisions

- Bid scope: national lots for generics distribution + cold-chain vaccines; Eastern Province anchored on Dammam hub. Central Region incumbent lots defended at improved service levels.

- Pricing: availability-bonus model priced into value-based pilot lots (per SIG-2026-06); flat unit-price bidding rejected. Floor margin set at framework +40bps vs 2024 award.

- OTIF evidence pack: Tatmeen readiness (87%) and stock-out reduction (-18% YoY) to be front-loaded in technical submission.

- Bid bond and working-capital impact (60-day NUPCO terms) confirmed within treasury headroom — CFO to reserve SAR 45M.

## Risks discussed

- Competitor aggression (Mohebi, DHL) on cold-chain lots; counter is -70C capability and integrated distribution+logistics offer.

- Concentration: winning national lots lifts government share further — Board risk appetite confirmed within R-03 tolerance, private-channel growth plan runs in parallel.

## Actions

| # | Action | Owner | Due |
| --- | --- | --- | --- |
| 1 | Final bid model incl. availability bonuses | CFO team | 15 Jul |
| 2 | Technical volume: cold-chain + Tatmeen evidence | CEO Pharma Logistics | 22 Jul |
| 3 | Legal review of value-based pilot T&Cs | Legal | 18 Jul |
| 4 | Board circular for bid approval | CEO office | 25 Jul |