## Decision_Log
ID | Finding / Item | Source | Decision | Owner | Approval status | Approved by | Date | Value (SAR) | Recovered to date (SAR) | Due | Status
RD-01 | Duplicate payment Premier Pharma INV-2026-0341 (wire + cheque) | H1 audit P1 | Recover from vendor via offset against Q3 invoices | AP Manager | Approved | CFO S. Al-Mahmoud | 2026-05-22 | 177188 | 88594 | 2026-09-30 | In progress
RD-02 | Duplicate-entity vendor Al-Rashid V-1142/V-1187 (same Tax ID + bank) | H1 audit P2 | Merge vendor records; block V-1187; controls fix in vendor onboarding | Procurement Dir. | Approved | BU CEO F. Al-Harbi | 2026-05-22 | 105000 | 0 | 2026-08-31 | In progress
RD-03 | Off-contract Quick Print spend (single e-mail approver) | H1 audit P3 | No-PO-no-pay from 1-Aug; competitive print tender | Marketing Dir. | Approved | BU CEO | 2026-05-22 | 420200 | 0 | 2026-08-01 | In progress
RD-04 | FG-2241 price variance 'emergency restock' @41 vs contract 32 | H1 audit P4 | Credit note requested from Gulf BioPharma; emergency-buy protocol | Procurement Dir. | Approved | CFO | 2026-05-22 | 30600 | 30600 | 2026-07-15 | Recovered
RD-05 | Missed 2/10 net 30 discounts Saudi Pharma | H1 audit P5 | Backfill AP clerk; discount diary automated in ERP | AP Manager | Approved | CFO | 2026-05-22 | 56500 | 0 | 2026-07-31 | In progress
RD-06 | Gulf Cold-Chain CPI+3% uncapped escalation (+22.2%) | H1 audit P6 | Renegotiate CT-2023-014 with insourcing BATNA (Dammam hub) | Head of Procurement | Approved | CEO K. Al-Rashed | 2026-06-03 | 250000 | 0 | 2026-09-30 | In negotiation
RD-07 | FX hedge HD-2026-019 not applied (Servier May payment) | H1 audit P7 | Treasury/AP system integration; hedge checklist on EUR runs | Group Treasurer | Approved | CFO | 2026-05-22 | 42912 | 0 | 2026-08-15 | In progress
RD-08 | Dormant credit CR-2024-091 Mediterranean Pharma | H1 audit P8 | Offset against July invoice cycle | AP Manager | Approved | CFO | 2026-05-22 | 128000 | 128000 | 2026-07-10 | Recovered
RD-09 | Historic: Premier duplicate Nov-2025 INV-2025-2841 | Historic review H1 | Combine with RD-01 vendor offset | AP Manager | Approved | CFO | 2026-06-14 | 96600 | 0 | 2026-09-30 | In progress
RD-10 | Historic: Bahr Freight double-billing Mar-May 2024 | Historic review H4 | Legal demand letter; vendor inactive — provision if no recovery by Q4 | Legal Counsel | Pending approval | — | 2026-06-14 | 198063 | 0 | 2026-10-31 | Open
RD-11 | Historic: Qassim co-location utilities unrecharged | Historic review H5 | Backdated intercompany recharge to Mizan Pharmacy Retail; group recharge policy | Group CFO | Approved | Capital Committee | 2026-06-09 | 4429534 | 4429534 | 2026-06-30 | Settled intercompany
RD-12 | Hijaz PKG-1101 price creep +19% since 2023 | Historic review H2 | Re-tender awarded 23-Jun; new supplier at SAR 8.20/unit | Head of Procurement | Approved | BU CEO | 2026-06-23 | 340000 | 0 | 2026-12-31 | Go-forward saving
RD-13 | KAUST contribution-negative account (12% rebate, 100-day pay) | Historic review H3 | Renegotiation mandate: tiered service pricing; rebate cap 6% | Head of Institutional Sales | Approved | Board (7-Jun mandate) | 2026-06-07 | 8240000 | 0 | 2026-09-30 | In negotiation
| TOTAL identified (excl. KAUST strategic) | [6 empty] | 6274597 | 4676728