# Group Synergy Programme — Charter

Sponsor: Group COO | Approved: ExCo 24 June 2026 | Target: ~SAR 86M/yr run-rate savings by 2028 (~+100bps consolidated BU EBITDA)

## Programmes and owners

| ID | Programme | 2025 addressable spend (SAR M) | Target saving (SAR M/yr) | Owner | First milestone |
| --- | --- | --- | --- | --- | --- |
| SYN-01 | Logistics insourcing to Mizan Pharma Logistics | 177 | 22 | COO | Gulf Cold-Chain renegotiation (RD-06) Q3 |
| SYN-02 | IT licences & cloud consolidation | 107 | 12 | Group CIO | ELA renewals Q4-2026 |
| SYN-03 | Facilities co-location + recharge policy | 312 | 15 | Group Property | Recharge standard live (CC-2026-08) — done |
| SYN-04 | Group energy: PPA + solar | 191 | 17 | Group COO | PPA RFP launch Q3 (CC-2026-09) |
| SYN-05 | Packaging category tower | 64 | 4.5 | Group Procurement | Hijaz re-tender awarded 23-Jun — done |
| SYN-06 | Group insurance programme | 31 | 4.7 | Group CFO | Broker RFP Sep; renewal Jan-2027 |
| SYN-07 | Finance shared services + AI agents | ~90 function cost | 11 | Group CFO | Tamween pilot complete; group design Q4 |

## Governance

- Monthly synergy tracker in StrategyOS; savings counted only when banked in BU budgets (no double counting with BU cost plans).

- Quarterly review at Capital Committee; annual reset in budget cycle.

- Proof-case discipline: each programme anchors on a validated finding from the Tamween dataset (e.g., Qassim recharge for SYN-03, Hijaz creep for SYN-05).